 Humber, Ford & Stoke Prior 

Group Parish Council

Minutes of the meeting of the 
Neighbourhood Development Plan Steering Committee
 held on Monday 12 January 2015 at 7.30pm in Risbury Village Hall
Present:
Cllr William Jackson (WJ) (Chairman)
Cllr Peter Lefroy-Owen (PLO)


Hugh Fowler Wright (HFW)
Cllr Ken Bemand (KB)

Cllr Alan Bathurst (AB)
With:
Bill Bloxsome (Planning Consultant) (BB), and Philip Brown (Clerk) (PB)
	Minute

	Topic
	Action

	NDP/180
	Apologies for Absence 
Received: Apologies from Iain Cholerton (IC), Peter Stovold (PS), Steph Wilson (SW), Mike Kimbery (MK),
	

	NDP/181
	Declarations of Interest and Dispensations
	

	(a)
	Noted: The declaration of interest from Cllr Steph Wilson given under minute NDP/104 also applied to this meeting. Cllr Wilson would be absent from meetings which considered development of planning policies.
	

	(b)
	There were no applications for dispensations under Standing Order 25(d).
	

	NDP/182
	Minutes of last meeting

Resolved: to approve the minutes of 15 December 2014.
	

	NDP/183
	Matters arising from the minutes (not covered elsewhere)
	

	
	None.
	

	NDP/184
	Public Participation

No members of the public were present.
	

	NDP/185
	Chairman’s comments and report

None. 
	

	NDP/186
	Budget Report

Noted: £2521 of the £5137 Lottery award had been spent to date, and spending had to be completed by 31/03/15 but a 6-month extension could be applied for. Remaining funds were earmarked for printing the draft plan and pre-referendum plan (£1898), consultation event costs (£134) and the website (£585).
	

	(a)
	Received: a budget report from the Clerk (Annexe NDP/186a). 

Noted: all £7000 of the Grant had been spent by 31 December, covering the planned activities.

Agreed: thanks to the Clerk for overseeing the spending within budget.
	

	(b)
	Resolved: to approve the End of Grant Monitoring Form, to be submitted to the Communities Development Foundation (Annexe NDP186b) 
	

	NDP/187
	Preparation of draft Plan (Project Stage 4)
	

	(a)
	Received: draft Plan version 3.2 (Minutes Annexe NDP/187).
	

	
	Agreed: PLO would email details of minor textual amendments to PB.
	PLO

	
	Agreed: Amendments to Policy HFSP5 and the explanatory text, to clarify the policy on Poplands Lane and Blacksmiths Lane as being outside the area for designated expansion of housing in Risbury (and the reasons for this) but that there was some scope for housing in Poplands Lane within the criteria of Core Strategy RA3 and the expanded definitions of HFSP7.
	PB

	
	Agreed: Other minor amendments to policies, and that the section on Monitoring and Implementation should be completed by PB and circulated.
	PB

	(b)
	Agreed: Following circulation of a revised draft, the complete draft should be sent to Herefordshire Council NP Team for comments and to ask them to undertake the Strategic Environmental Assessment; also to put the complete draft on the agenda for Council on 21 January 2015 for their comments (indicating that the draft was not for general public availability at this stage). 
	PB

	NDP/188
	Pre-submission (Regulation 14) Consultation (Project Stage 5).
Agreed: Unless Herefordshire NP Team or Council had major concerns or reservations about the complete draft, the 6-week Regulation 14 Consultation should be planned for mid-March to the end of April.  Estimates for printing copies for every household would be obtained, and the Annual Parish Meeting planned to be held in the School with the NDP as the major item.  Comments at this statutory consultation would have to be traceable and auditable, so comment forms would require respondents to identify themselves.
	Discuss at next meeting

	NDP/189
	Matters for information or future business

Noted: The draft Leominster Area Neighbourhood Plan was out for Regulation 14 Consultation from 15 December, although we had not been formally notified of this as an adjoining local council.  Commenting on other NDPs was not within the remit of the Committee, and the Leominster NDP would be on the Council agenda for 21 January 2015.
	PB

	NDP/190
	Meeting dates
Agreed: The next meeting would be held on Wednesday 4 February 2015.
	PB

	
	The meeting closed at 9.00pm.
	


Signed ................................... (Chairman)
Date ...........................
PAGE  
HF&SP NDP Steering Committee
 page 38

