Humber, Ford & Stoke Prior 

Group Parish Council

Minutes of the meeting of the 
Neighbourhood Development Plan Steering Committee
 held on Wednesday 12 March 2014 at 7.30pm in Risbury Village Hall
Present:
Alan Bathurst (AB)
Cllr Ken Bemand (KB)


Iain Cholerton (IC)
Hugh Fowler-Wright (HF)


Cllr William Jackson (WJ)
Cllr Peter Lefroy-Owen (PLO)

Peter Stovold (PS)
Cllr Stephanie Wilson (SW)
with:
Philip Brown (PB) (Clerk)

	Minute

	Topic
	Action

	NDP/52
	Apologies for Absence 
Received: Apologies from Mike Kimbery (MK). 
	

	NDP/53

	Declarations of Interest and Dispensations

There were no declarations of interest in agenda items.

There were no applications for dispensations from the rules on participation by members with a disclosable pecuniary interest.
	

	NDP/54
	Minutes of last meeting

Resolved: to approve the minutes of 12 February 2014.
	

	NDP/55
	Matters arising from the minutes (not covered elsewhere)

Reported: The acceptance forms and financial details for the Lottery grant had been submitted on 18 February but the Lottery office had said that payment of grants was currently taking up to three months. PB had included on the 19 March Council agenda authorisation of required spending from Lottery/grant funds so that activities would be not be delayed.
	

	NDP/56
	Public Participation

No members of the public were present.
	

	NDP/57
	Chairman’s comments and report

Reported: The Working Group had good progress with planning the April events. An event in the school for the children was proposed – details to be arranged.

Reported: Eardisley’s project manager had invited WJ, MK and PB to meet on 25 March to share their experience.
	WJ, MK, PB attend Eardisley meeting

	NDP/58
	Project Manager’s Report and Project Plan
Received and agreed: a, updated project plan from MK (Minutes Annexe NDP58).
Noted: Steering Committee meetings would be held on Wed 16 April following the public events and Mon 28 April to finalise the questionnaire.
	

	NDP/59
	April consultation events (Project Stage 3)

Reported: the Working Group had met three times and prepared a proposal for the detailed organisation of the initial consultation events in early April to be called Your Community, Your Future.

Received and agreed: The proposal for the events (Minutes Annexe NDP/59).

Agreed: WJ would speak with Matt Lewis about a school-time activity to involve the children prior to the childrens’ questionnaire going out.

Agreed: IC/PB to order the large-scale maps from Hoople at a cost of £132 + VAT, to include floodplain, SSSIs etc.

Agreed: IC to obtain four more large pin-boards with a budget of £80 for this, and all members to try to find easels or other means of displaying these.

Agreed: PB to draft content of publicity leaflet, Pump advert and introductory presentation by 16 March, for PS to finalise design.
Noted: the Working Group would meet on 17 March for a mock run-through of the event format, trialling this on some residents.
	WJ agree event with School

IC/PC order maps

IC obtain boards

PB/PS draft publicity



	NDP/60
	Questionnaire (Project Stage 3)

Noted: the second version of the questionnaire had been circulated to members following the last meeting.
Received: a revised draft of Section Six – our future housing (Minutes Annexe NDP/60).

Agreed: to include Sport & Recreation as a land-use category and consider re-instating Intensive Agriculture as a category.
Agreed: although the final version of the questionnaire would be guided by comments from the April events, its format should be developed now and the content adjusted in the final designed version. 

Agreed: PLO would discuss the format of the questionnaire with Gemma Webster and Data Orchard (noting there is a budget of £400 for this), and PS would finalise the design and organise printing (budget of £840 + VAT for this).
	PLO discuss design with NPT & Data Orchard

	NDP/61
	Publicity and Website
Agreed: PB to circulate residents with a summary update on progress with the project, and this to be placed on the website.
Agreed: Development of specific NDP web-pages was a priority, and funding of £1400 +VAT would be available for this pending payment of the Lottery grant.  WJ would obtain quotes for this and report to the Council meeting on 19 March to obtain authorisation to go ahead with the website development.
	PB circulate update to residents

WJ get quotes for website

	NDP/62
	Matters for information or future business

None.
	

	NDP/63
	Meeting dates

Resolved: to hold future meetings on:
Wednesday 16 April 2014 at 7.30pm (Stoke Prior VH)

Monday 28 April 2014 at 7.30pm (venue TBC).

	PB confirm venues

	
	The meeting closed at 8.33pm.
	


Signed ................................... (Chairman)
Date ...........................
PAGE  
HF&SP NDP Steering Committee
 page 11

