#### Grant Application:

| NP Application Ref | App-00603 |
| --- | --- |
| Neighbourhood Organisation | Humber, Ford & Stoke Prior Group Parish Council |
| Main Point of Contact | Philip Brown |
| Total Grant Calculated | £7,011.00 |
| Total value of grant | £7,000.00 |
| Why grant is needed | From the initial work done on understanding what an NDP is and how this is produced, we are aware that this is a major project for a small group parish. The community has given its overwhelming backing to going ahead with a Plan. The Council has reserves of only £3500, of which £1200 are set against specific risks, and the remainder is required as prudent provision against unknown risks or costs. Without any external funding, therefore, we would barely be able to afford the most basic costs of evidence-gathering, consultation and community-engagement, and be unable to afford any external professional advice. The project plan has identified all the stages of the project, and a budget of £7500 has been prepared to undertake a basic job at all these stages. We are applying for another grant from Lottery Awards for All to enhance the community engagement with the NDP. Lottery funding will enable us to do a better job of engaging with our community in producing the plan (for example by being able to afford professional printing, organising larger consultation events, and developing an NDP website). |
| How it will help to move plan forward | The grant would be used to meet the essential costs of producing a Plan up until December 2014, which is when we aim to have the final Plan ready for submission, covering: Administrative costs, such as hire of venues for monthly Steering Committee meetings (held in public). Consultation and community engagement, including hire of venues, materials for presenting the issues (including large-scale maps), publicity and other costs. Professional advice and assistance: (1) expert help in developing questionnaires to be given to all residents, and professional collation and analysis of these, leading to a report; (2) expert help from a professional planning consultant in identifying issues and options, and then in writing planning policies and reviewing these. Printing costs: a questionnaire for all residents, and draft documents for public information, including a copy of the draft plan (at pre-submission stage) for every household. |
| Commissioned experts | We intend to commission a local Community Interest Company, Data Orchard (Company No. 08674626), Church House, Allensmore, Herefordshire HR6 9AG, to assist with the development of residents’ questionnaires, and the professional analysis of this (see attached emailed quotation). We also intend to commission a professional planning consultant to provide advice on developing and writing the Plan: Andrew Ford (DipTP, DipUD, MPhil, MRTPI) engaged through Community First in Herefordshire and Worcestershire (Company No.2504158) (see attached quotation). |
| VAT registered | No |
| Supporting Documents | http://www.clicktools.com/dashboard/store?id=3sjeb2thhjb_1nd3kimrjwry1_3sjeb2thhjc |

#### 2. Funding to produce main elements of plan:

| 2. Main Elements of Plan | Yes |  |  |
| --- | --- | --- | --- |
| 2.1 Type of Activity | Administration costs | 2.1 Cost | £232.00 |
| 2.1 Budget Breakdown | Steering Committee meetings (hall hire, 27hrs@£6): £162; General administrative costs (copying, postage.stationery): £70. |  |  |
| 2.2 Type of Activity | Consultation and community engagement | 2.2 Cost | £680.00 |
| 2.2 Budget Breakdown | Hire of village halls (6 events,30hrs@£6):£180; Refreshments for 8 events (833 attendees@12p:£100; Large-scale maps (14 copies of A0maps):£220; Materials for consultation events: £120; Promotion & publicity for 8 events (100 laminated posters@60p):£60 |  |  |
| 2.3 Type of Activity | Professional advice and assistance on questionnaires | 2.3 Cost | £3,368.00 |
| 2.3 Budget Breakdown | Questionnaire development & design:£400; response collation and analysis: £2979 (see attached estimate) |  |  |
| 2.4 Type of Activity | Professional planning advice and assistance | 2.4 Cost | £1,820.00 |
| 2.4 Budget Breakdown | 52 hours @ £35 (see attached quote): Advice on identifying issues & options (21hrs); Review of draft plan and technical writing (21hrs); advice on pre-submission plan (10hrs) |  |  |
| 2.5 Type of Activity | Printing costs | 2.5 Cost | £900.00 |
| 2.5 Budget Breakdown | In-house copying of evidence/drafts (3570 copies@1.4p): £50; 725 questionnaires @ 11p: £80; 350 'Issues & Options' consultation paper @£1: £350; 350 copies of pre-submission Draft Plan @£1.20: £420 |  |  |
|  |  | 2. Sub-Total Grant | £7,000.00 |

#### Application Outcome:

| Amount Panel Agreed | £7,000.00 |
| --- | --- |
| Planned Grant Start Date | 31/03/2014 |
| Planned Grant Finish Date | 31/12/2014 |